## Project Budget
[8 empty] | Labor | 108000 | 101200
PROJECT BUDGET | [7 empty] | Materials | 63000 | 59500
[8 empty] | Equipment | 16000 | 15200
Project Name: | Office Renovation Phase 2 |  | Client: | Acme Corporation |  | Total Budget: | 268000 | Subcontractors | 40000 | 33500
Project Manager: | Sarah Williams |  | Department: | Facilities |  | Total Actual: | 235500 | Travel | 7000 | 6300
Start Date: | 2026-01-15 |  | Budget Approved: | 2026-03-01 |  | Variance: | 32500 | Software | 10500 | 9000
End Date: | 2026-09-30 |  | Status: | In Progress |  | % Spent: | 87.87% | Overhead | 8500 | 7800
[8 empty] | Contingency | 15000 | 3000
# | Description | Budgeted | Actual | Variance | % Spent | % of Total | Notes
1 | Labor
1.1 | Project Manager | 25000 | 22000 | 3000 | 88% | 9.328% | 60% time allocation
1.2 | Architects & Designers | 18000 | 17500 | 500 | 97.22% | 6.716%
1.3 | Construction Workers | 45000 | 42000 | 3000 | 93.33% | 16.79%
1.4 | Electricians | 12000 | 11500 | 500 | 95.83% | 4.478%
1.5 | Plumbers | 8000 | 8200 | -200 | 102.5% | 2.985% | Overtime needed
| Labor Subtotal | 108000 | 101200 | 6800 | 93.7% | 40.3%
2 | Materials
2.1 | Building Materials | 35000 | 33000 | 2000 | 94.29% | 13.06% | Lumber, drywall, etc.
2.2 | Flooring | 15000 | 14200 | 800 | 94.67% | 5.597%
2.3 | Paint & Finishes | 5000 | 4800 | 200 | 96% | 1.866%
2.4 | Hardware & Fixtures | 8000 | 7500 | 500 | 93.75% | 2.985%
| Materials Subtotal | 63000 | 59500 | 3500 | 94.44% | 23.51%
3 | Equipment
3.1 | Equipment Rental | 10000 | 9500 | 500 | 95% | 3.731% | Crane, scaffolding
3.2 | Tools & Supplies | 4000 | 3800 | 200 | 95% | 1.493%
3.3 | Safety Equipment | 2000 | 1900 | 100 | 95% | 0.7463%
| Equipment Subtotal | 16000 | 15200 | 800 | 95% | 5.97%
4 | Subcontractors
4.1 | HVAC Contractor | 22000 | 21000 | 1000 | 95.45% | 8.209%
4.2 | Glass & Windows | 12000 | 12500 | -500 | 104.2% | 4.478% | Custom sizes
4.3 | Landscaping | 6000 | 0 | 6000 | 0% | 2.239% | Not started
| Subcontractors Subtotal | 40000 | 33500 | 6500 | 83.75% | 14.93%
5 | Travel & Logistics
5.1 | Site Transportation | 3000 | 2800 | 200 | 93.33% | 1.119%
5.2 | Material Delivery | 4000 | 3500 | 500 | 87.5% | 1.493%
| Travel & Logistics Subtotal | 7000 | 6300 | 700 | 90% | 2.612%
6 | Software & Permits
6.1 | CAD Software License | 2500 | 2500 | 0 | 100% | 0.9328% | Annual
6.2 | Building Permits | 5000 | 5000 | 0 | 100% | 1.866%
6.3 | Inspection Fees | 3000 | 1500 | 1500 | 50% | 1.119% | 50% complete
| Software & Permits Subtotal | 10500 | 9000 | 1500 | 85.71% | 3.918%
7 | Overhead
7.1 | Insurance | 4000 | 4000 | 0 | 100% | 1.493%
7.2 | Utilities (Site) | 3000 | 2600 | 400 | 86.67% | 1.119%
7.3 | Office Supplies | 1500 | 1200 | 300 | 80% | 0.5597%
| Overhead Subtotal | 8500 | 7800 | 700 | 91.76% | 3.172%
8 | Contingency
8.1 | Contingency Reserve | 15000 | 3000 | 12000 | 20% | 5.597% | 10% of total budget
| Contingency Subtotal | 15000 | 3000 | 12000 | 20% | 5.597%
| PROJECT TOTAL | 268000 | 235500 | 32500 | 87.87% | 100%

## Monthly Tracking
MONTHLY BUDGET TRACKING
Office Renovation Phase 2
Category | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Labor | 8000 | 9000 | 10000 | 12000 | 14000 | 13000 | 12000 | 11000 | 10500 | 0 | 0 | 0 | 99500
Materials | 2000 | 5000 | 8000 | 10000 | 8000 | 6000 | 5000 | 3000 | 2500 | 0 | 0 | 0 | 49500
Equipment | 1500 | 2000 | 2000 | 2000 | 1500 | 1500 | 1500 | 1000 | 1000 | 0 | 0 | 0 | 14000
Subcontractors | 0 | 3000 | 5000 | 5000 | 5000 | 5000 | 5000 | 3000 | 2000 | 0 | 0 | 0 | 33000
Travel & Logistics | 500 | 700 | 800 | 800 | 700 | 700 | 700 | 600 | 500 | 0 | 0 | 0 | 6000
Software & Permits | 2500 | 500 | 500 | 500 | 1500 | 500 | 500 | 500 | 1500 | 0 | 0 | 0 | 8500
Overhead | 800 | 800 | 850 | 900 | 900 | 850 | 850 | 800 | 800 | 0 | 0 | 0 | 7550
Contingency | 0 | 0 | 500 | 0 | 1000 | 0 | 500 | 0 | 1000 | 0 | 0 | 0 | 3000
MONTHLY TOTAL | 15300 | 21000 | 27650 | 31200 | 32600 | 27550 | 26050 | 19900 | 19800 | 0 | 0 | 0 | 221050
Cumulative Spend | 15300 | 36300 | 63950 | 95150 | 127750 | 155300 | 181350 | 201250 | 221050 | 221050 | 221050 | 221050 | 221050
Total Budget | [12 empty] | 268000
Budget Remaining | [12 empty] | 46950