## Construction Schedule
CONSTRUCTION SCHEDULE
Project Name: | Sample Construction Project |  | Start Date: | 2026-04-06
Project Manager: | John Smith |  | End Date: | 2026-10-12
Task / Phase | Start Date | End Date | Duration | % Complete | Assigned To | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26
[6 empty] | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
Site Survey & Assessment | 2026-04-06 | 2026-04-20 | 14 | 100% | Acme Survey
Permits & Approvals | 2026-04-13 | 2026-05-04 | 21 | 75% | Owner
SITE PREPARATION
Demolition & Clearing | 2026-04-27 | 2026-05-11 | 14 | 50% | GradePro
Grading & Excavation | 2026-05-04 | 2026-05-18 | 14 | 25% | GradePro
Utility Connections | 2026-05-11 | 2026-06-01 | 21 | 0% | CityWorks
FOUNDATION
Footings | 2026-05-25 | 2026-06-08 | 14 | 0% | SolidBase Inc.
Foundation Walls | 2026-06-01 | 2026-06-15 | 14 | 0% | SolidBase Inc.
Slab / Basement | 2026-06-08 | 2026-06-22 | 14 | 0% | SolidBase Inc.
FRAMING
Floor Framing | 2026-06-22 | 2026-07-06 | 14 | 0% | FrameRight
Wall Framing | 2026-06-29 | 2026-07-13 | 14 | 0% | FrameRight
Roof Framing | 2026-07-06 | 2026-07-20 | 14 | 0% | FrameRight
EXTERIOR
Roofing | 2026-07-20 | 2026-08-03 | 14 | 0% | TopCover
Siding & Exterior Trim | 2026-07-27 | 2026-08-10 | 14 | 0% | ExteriorPros
WINDOWS & DOORS
Window Installation | 2026-08-03 | 2026-08-10 | 7 | 0% | ExteriorPros
Door Installation | 2026-08-10 | 2026-08-17 | 7 | 0% | ExteriorPros
MEP ROUGH-IN
Plumbing Rough-In | 2026-08-10 | 2026-08-24 | 14 | 0% | AllTrades MEP
Electrical Rough-In | 2026-08-10 | 2026-08-24 | 14 | 0% | AllTrades MEP
HVAC Rough-In | 2026-08-17 | 2026-08-31 | 14 | 0% | AllTrades MEP
INTERIOR FINISHES
Insulation & Drywall | 2026-08-24 | 2026-09-07 | 14 | 0% | DryWall Plus
Interior Painting | 2026-08-31 | 2026-09-14 | 14 | 0% | FinishLine
Flooring | 2026-09-07 | 2026-09-21 | 14 | 0% | FinishLine
FINAL INSTALLATIONS
Cabinetry & Countertops | 2026-09-14 | 2026-09-21 | 7 | 0% | FinishLine
Plumbing Fixtures | 2026-09-14 | 2026-09-21 | 7 | 0% | AllTrades MEP
Electrical Fixtures | 2026-09-21 | 2026-09-28 | 7 | 0% | AllTrades MEP
Appliance Installation | 2026-09-21 | 2026-09-28 | 7 | 0% | BuildRight
CLOSEOUT
Final Inspections | 2026-09-28 | 2026-10-05 | 7 | 0% | Owner
Punch List | 2026-09-28 | 2026-10-05 | 7 | 0% | BuildRight
LANDSCAPING
Grading & Drainage | 2026-09-28 | 2026-10-05 | 7 | 0% | LandscapeCo
Planting & Hardscaping | 2026-09-28 | 2026-10-05 | 7 | 0% | LandscapeCo
Final Cleanup & Handover | 2026-10-05 | 2026-10-12 | 7 | 0% | BuildRight
Formulas:
End Date = [Sample Construction Project]+14