## Critical_Path
CRITICAL PATH METHOD (CPM) | [9 empty] | GANTT CHART
Enter task details in blue cells. Forward/backward pass and float calculate automatically.
[10 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
ID | Task Name | Duration | Predecessors | ES | EF | LS | LF | Float | Critical?
1 | Project Kickoff | 0 |  | 0 | 0 | 0 | 0 | 0 | YES
2 | Requirements Gathering | 3 | 1 | 0 | 3 | 0 | 3 | 0 | YES
3 | Site Survey | 2 | 1 | 0 | 2 | 6 | 8 | 6
4 | Design Phase | 5 | 2 | 3 | 8 | 3 | 8 | 0 | YES
5 | Permits & Approvals | 3 | 3 | 2 | 5 | 8 | 11 | 6
6 | Procurement | 3 | 4 | 8 | 11 | 8 | 11 | 0 | YES
7 | Foundation Work | 6 | 5,6 | 11 | 17 | 11 | 17 | 0 | YES
8 | Structural Build | 8 | 7 | 17 | 25 | 17 | 25 | 0 | YES
9 | Electrical & Plumbing | 5 | 7 | 17 | 22 | 20 | 25 | 3
10 | Interior Finishing | 4 | 8,9 | 25 | 29 | 25 | 29 | 0 | YES
11 | Inspection & Handover | 2 | 10 | 29 | 31 | 29 | 31 | 0 | YES
12 | Project Closeout | 1 | 11 | 31 | 32 | 31 | 32 | 0 | YES
Project Duration: |  | 32 | days | Avg Duration: | 3.5
Critical Path Tasks: |  | 9 |  | Total Tasks: | 12