## Instructions
RACI MATRIX — INSTRUCTIONS
What is a RACI Matrix?
A RACI matrix clarifies roles and responsibilities for each task in a project.
Each task is assigned exactly one Accountable owner, with supporting roles.
RACI Definitions:
R — Responsible: The person who does the work to complete the task.
A — Accountable: The person who approves/owns the outcome (one per task).
C — Consulted: People whose input is sought before a decision or action.
I — Informed: People who are kept updated on progress or decisions.
How to Use This Template:
1. Go to the 'RACI Matrix' sheet.
2. Update the Project Name in cell C4.
3. Edit tasks in column C (rows 10-22). Add/remove rows as needed.
4. Set the Phase for each task using the dropdown in column D.
5. Assign R, A, C, or I to each role using the dropdowns (columns E-K).
6. Update role/column headers (row 9) to match your team's roles.
7. The 'A Count' column (L) validates that each task has exactly one Accountable.
8. The Role Summary section (rows 25-28) auto-calculates assignment counts.
Tips:
• Every task should have exactly one 'A'. The A Count column flags violations.
• Minimize the number of R's per task to maintain clear ownership.
• Use 'C' sparingly — too many consulted parties slows decisions.
• Review the matrix with your team to ensure alignment.

## RACI-Matrix
RACI MATRIX
Project: | Sample Project
LEGEND |  |  | R | Responsible — Does the work | C | Consulted — Provides input
|  |  | A | Accountable — Owns the decision | I | Informed — Kept in the loop
# | Task / Deliverable | Phase | PM | Dev Lead | Designer | QA Lead | Stakeholder | Finance | Legal | ✓ A Count
1 | Define project scope | Planning | A | C | C | I | R | I | I | 1
2 | Gather requirements | Planning | A | R | C | I | C | I | I | 1
3 | Create project plan | Planning | R | C | I | I | A | I | I | 1
4 | Budget approval | Planning | R | I | I | I | A | C | I | 1
5 | UI/UX design | Design | I | C | R | C | A | I | I | 1
6 | Design review & approval | Design | C | C | R | I | A | I | I | 1
7 | Backend development | Development | I | R | I | C | A | I | I | 1
8 | Frontend development | Development | I | R | C | C | A | I | I | 1
9 | Integration testing | Testing | I | C | I | R | A | I | I | 1
10 | User acceptance testing | Testing | C | I | I | R | A | I | I | 1
11 | Security audit | Testing | I | C | I | I | A | I | R | 1
12 | Deployment to production | Launch | A | R | I | C | I | I | I | 1
13 | Post-launch monitoring | Launch | A | R | I | R | I | I | I | 1
ROLE SUMMARY
Responsible (R) |  |  | 2 | 5 | 2 | 3 | 1 | 0 | 1
Accountable (A) |  |  | 4 | 0 | 0 | 0 | 9 | 0 | 0
Consulted (C) |  |  | 2 | 6 | 3 | 4 | 1 | 1 | 0
Informed (I) |  |  | 5 | 2 | 8 | 6 | 2 | 12 | 12