## Project-Timeline
Project Timeline
Project Start: | 2026-03-02 |  | Today: | 2026-03-20
[7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Task / Milestone | Start Date | End Date | Duration | % Done | Status | Owner | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10
Phase 1: Planning
Define project scope | 2026-03-02 | 2026-03-09 | 7 | 100% | Complete | Alex
Stakeholder analysis | 2026-03-02 | 2026-03-16 | 14 | 100% | Complete | Jordan
Requirements gathering | 2026-03-09 | 2026-03-30 | 21 | 75% | In Progress | Sam
Create project plan | 2026-03-16 | 2026-03-30 | 14 | 50% | In Progress | Alex
Phase 2: Design
System architecture | 2026-03-30 | 2026-04-20 | 21 | 25% | In Progress | Jordan
UI/UX design | 2026-03-30 | 2026-04-27 | 28 | 10% | In Progress | Chris
Database design | 2026-04-06 | 2026-04-20 | 14 | 0% | Not Started | Sam
Design review | 2026-04-27 | 2026-05-04 | 7 | 0% | Not Started | Team
Phase 3: Development
Frontend development | 2026-05-04 | 2026-06-15 | 42 | 0% | Not Started | Chris
Backend development | 2026-05-04 | 2026-06-22 | 49 | 0% | Not Started | Sam
API integration | 2026-05-25 | 2026-06-22 | 28 | 0% | Not Started | Jordan
Phase 4: Testing & Launch
QA testing | 2026-06-22 | 2026-07-13 | 21 | 0% | Not Started | QA Team
User acceptance testing | 2026-07-06 | 2026-07-20 | 14 | 0% | Not Started | Stakeholders
Bug fixes | 2026-07-13 | 2026-07-27 | 14 | 0% | Not Started | Team
Launch preparation | 2026-07-20 | 2026-07-27 | 7 | 0% | Not Started | Alex
GO LIVE ★ | 2026-08-03 | 2026-08-03 | 0 | 0% | Not Started | Team
Legend: | [6 empty] | W2: Completed; W5: Remaining; W8: Today (see F4)
Status: | [6 empty] | W1: ●; W2: Complete; W4: ●; W5: In Progress; W7: ●; W8: Not Started