## WBS
Work Breakdown Structure (WBS)
Project Name: | Website Redesign Project |  | Project Manager: | Sarah Johnson
Start Date: | 2026-03-01 |  | Target End: | 2026-06-30
WBS # | Task Name | Owner | Start Date | End Date | Duration | Status | % Complete | Priority
1 | Planning & Discovery |  | 2026-03-01 | 2026-03-21 | 21 | Complete | 100% | High
1.1 | Stakeholder interviews | Sarah J. | 2026-03-01 | 2026-03-07 | 7 | Complete | 100% | High
1.2 | Requirements gathering | Sarah J. | 2026-03-08 | 2026-03-14 | 7 | Complete | 100% | High
1.3 | Competitive analysis | Mike T. | 2026-03-08 | 2026-03-14 | 7 | Complete | 100% | Medium
1.4 | Project plan approval | Sarah J. | 2026-03-15 | 2026-03-21 | 7 | Complete | 100% | High
2 | Design |  | 2026-03-22 | 2026-04-18 | 28 | In Progress | 50% | High
2.1 | Wireframes | Alex R. | 2026-03-22 | 2026-04-04 | 14 | Complete | 100% | High
2.2 | Visual mockups | Alex R. | 2026-04-05 | 2026-04-11 | 7 | In Progress | 50% | High
2.3 | Design review & approval | Sarah J. | 2026-04-12 | 2026-04-18 | 7 | Not Started | 0% | Medium
3 | Development |  | 2026-04-19 | 2026-05-30 | 42 | Not Started | 0% | High
3.1 | Front-end development | Chris L. | 2026-04-19 | 2026-05-09 | 21 | Not Started | 0% | High
3.1.1 | Homepage | Chris L. | 2026-04-19 | 2026-04-25 | 7 | Not Started | 0% | High
3.1.2 | Inner pages | Chris L. | 2026-04-26 | 2026-05-02 | 7 | Not Started | 0% | Medium
3.1.3 | Responsive design | Chris L. | 2026-05-03 | 2026-05-09 | 7 | Not Started | 0% | Medium
3.2 | Back-end development | Dev Team | 2026-05-03 | 2026-05-23 | 21 | Not Started | 0% | High
3.3 | CMS integration | Dev Team | 2026-05-17 | 2026-05-30 | 14 | Not Started | 0% | Medium
4 | Testing & Launch |  | 2026-05-31 | 2026-06-30 | 31 | Not Started | 0% | High
4.1 | QA testing | QA Team | 2026-05-31 | 2026-06-13 | 14 | Not Started | 0% | High
4.2 | User acceptance testing | Sarah J. | 2026-06-14 | 2026-06-20 | 7 | Not Started | 0% | High
4.3 | Bug fixes | Dev Team | 2026-06-14 | 2026-06-27 | 14 | Not Started | 0% | High
4.4 | Go-live | Sarah J. | 2026-06-28 | 2026-06-30 | 3 | Not Started | 0% | High
Project Summary
Total Tasks: | 17
Completed: | 6
In Progress: | 2
Not Started: | 13
Overall Progress: | 37.5%