## Risk-Matrix
RISK ASSESSMENT MATRIX
IMPACT
|  | Negligible | Minor | Moderate | Major | Catastrophic
|  | 1 | 2 | 3 | 4 | 5
Almost Certain | 5 | 5 | 10 | 15 | 20 | 25
Likely | 4 | 4 | 8 | 12 | 16 | 20
Possible | 3 | 3 | 6 | 9 | 12 | 15
Unlikely | 2 | 2 | 4 | 6 | 8 | 10
Rare | 1 | 1 | 2 | 3 | 4 | 5
RISK LEVELS: |  | Low (1-4) | Medium (5-9) | High (10-16) | Critical (17-25)
RISK REGISTER
ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Strategy | Owner | Status | Due Date
R-001 | Data breach from external attack | Cybersecurity | 3 | 5 | 15 | High | Implement multi-factor authentication | IT Director | Open | 2026-06-30
R-002 | Key supplier goes out of business | Supply Chain | 2 | 4 | 8 | Medium | Diversify supplier base; maintain safety stock | Procurement Lead | In Progress | 2026-05-15
R-003 | Regulatory compliance failure | Legal / Compliance | 3 | 4 | 12 | High | Quarterly compliance audits; legal review | Compliance Officer | Open | 2026-04-30
R-004
R-005
R-006
R-007
R-008
R-009
R-010