## FMEA
FMEA Template
Failure Mode and Effects Analysis
CURRENT ANALYSIS | [8 empty] | RECOMMENDED ACTIONS
Process Step / Function | Potential Failure Mode | Potential Effect(s) | SEV | Potential Cause(s) | OCC | Current Controls | DET | RPN | Recommended Action | Responsible | Target Date | New SEV | New OCC | New DET | New RPN
Assembly | Wrong part installed | Product malfunction | 8 | Untrained operator | 5 | Visual inspection | 6 | 240 | Implement barcode scan | J. Smith | 2026-04-15 | 8 | 2 | 3 | 48
Assembly | Loose fastener | Safety hazard | 9 | Insufficient torque | 4 | Torque wrench audit | 5 | 180 | Add torque verification | M. Jones | 2026-04-30 | 9 | 2 | 2 | 36
Welding | Incomplete weld | Structural failure | 10 | Worn electrode | 3 | Periodic replacement | 7 | 210 | Automated weld monitoring | R. Davis | 2026-05-15 | 10 | 1 | 2 | 20
Painting | Paint adhesion failure | Cosmetic defect | 5 | Improper surface prep | 6 | Surface roughness test | 4 | 120 | Pre-treatment validation | A. Wilson | 2026-05-01 | 5 | 3 | 2 | 30
Inspection | Missed defect | Customer complaint | 7 | Inspector fatigue | 4 | Double check system | 6 | 168 | Automated optical insp. | T. Brown | 2026-06-01 | 7 | 2 | 2 | 28

## Rating-Scales
FMEA Rating Scales Reference
SEVERITY (SEV) |  | OCCURRENCE (OCC) |  | DETECTION (DET)
Rating | Description | Rating | Description | Rating | Description
1 | No effect | 1 | Almost impossible (< 1 in 1,500,000) | 1 | Almost certain to detect
2 | Very minor effect | 2 | Very remote | 2 | Very high detection likelihood
3 | Minor effect | 3 | Remote | 3 | High detection likelihood
4 | Low effect on performance | 4 | Very low | 4 | Moderately high
5 | Moderate effect | 5 | Low | 5 | Moderate
6 | Significant performance degradation | 6 | Moderate | 6 | Low detection likelihood
7 | System inoperable (minor) | 7 | Moderately high | 7 | Very low
8 | System inoperable (major) | 8 | High | 8 | Remote detection chance
9 | Potential safety issue with warning | 9 | Very high | 9 | Very remote
10 | Safety hazard without warning | 10 | Almost certain (≥ 1 in 2) | 10 | Cannot detect / no control
RPN COLOR CODING
< 50 | Low Risk
50 – 100 | Medium Risk
101 – 200 | High Risk
> 200 | Critical Risk